Market Research & Go-To-Market Plan Enhanced Rock Weathering (ERW) Pilot — India 10,000 MT Rock Powder Deployment Roadmap for Verified Carbon Removal Credits

# Executive Summary

This report presents a comprehensive Market Research and Go-To-Market (GTM) Case Study for an Enhanced Rock Weathering (ERW) pilot in India, focused on deploying 10,000 metric tons (MT) of basalt rock powder across selected agricultural sites in Madhya Pradesh to explore the feasibility of measurable and scalable carbon removal.

The report covers six integrated workstreams — target-setting and budgeting, site identification, ground operations, testing and MRV, data analysis and modeling, and project registration — providing a data-driven roadmap for evaluating and planning an ERW pilot.

| KEY METRIC | VALUE / STATUS |
| --- | --- |
| Deployment Target | 10,000 MT of basalt rock powder |
| Pilot Location | Madhya Pradesh, India — West MP & Central MP zones |
| Primary District | Khandwa (Bhavsinghpura Basalt Quarry as supply source) |
| Area Covered | ~500 hectares at 20 MT/ha application rate |
| ERW Credit Price | $270–500 per tCO₂ (premium durable removal credits) |
| Estimated Landed Cost | ₹915/MT ¦ Total: ₹91.5 lakh for 10,000 MT |
| Go/No-Go Decision | GO — subject to credible MRV and certification |
| Pilot Duration | 6 months (setup to initial CO₂ removal estimate) |

# Implementation Flow Overview

The ERW pilot follows a structured, sequential six-stage implementation framework, from target-setting and site identification through to carbon credit registration. Each stage is designed to feed measurable outputs into the next, ensuring a rigorous, data-driven pathway to verified carbon removal credits.

| 01 | Target & Budgeting Set the 10,000 MT deployment target based on ERW market demand trends and premium credit pricing |
| --- | --- |
| 02 | Site Identification Shortlist agricultural regions using soil type, crop patterns, farmer readiness, logistics, and weathering potential. |
| 03 | Ground Operations Execute rock powder procurement, transport, farmer coordination, field application, and deployment tracking. |
| 04 | Testing & Sampling Collect baseline and post-application soil, water, and crop samples to measure chemical changes and carbon removal indicators. |
| 05 | Data Analysis & Modeling Analyze field data using scientific models to estimate carbon removal, environmental impact, and credit generation potential. |
| 06 | Registration Prepare MRV documentation and verification data required for carbon credit registration and certification. |

# 1. Target and Budgeting

The project target and budget form the strategic foundation of the ERW pilot. This section establishes the commercial rationale for the 10,000 MT rock powder deployment and confirms a Go decision for the pilot based on market demand and credit pricing analysis.

## 1.1 ERW Global Demand Study

According to the 2025 CDR Survey by CDR.fyi and Sylvera, buyer interest in ERW is projected to rise from 15% to 42% a near-threefold increase — indicating strong future market potential and growing institutional confidence in durable carbon removal solutions.

| Metric | Current | Projected |
| --- | --- | --- |
| Buyer Interest in ERW | 15% | 42% |
| Credit Type | Durable Carbon Removal | Durable Carbon Removal |
| Market Confidence | Growing | Strong |

## 1.2 ERW Credit Price Analysis

ERW credits command a significant premium in the voluntary carbon market due to their durable, measurable, and scientifically verifiable nature. Current market prices range from $270 to $500 per ton of CO₂ removed, depending on MRV quality, certification standards, and overall project reliability.

## 1.3 Go/No-Go Decision

Based on the demand growth trajectory and premium credit pricing, the Varaha ERW pilot is commercially viable and scientifically feasible. The following decision has been reached:

GO DECISION — The ERW pilot is approved to proceed, subject to credible MRV implementation and third-party certification.

# 2. Site Identification

Site identification follows a two-stage screening process: a national-level opportunity screening to identify high-potential states, followed by a district-level suitability analysis using a weighted Site Suitability Index (SSI).

## 2.1 India-Level ERW Opportunity Screening

India’s ERW potential is assessed using a broad opportunity score based on five key parameters: basalt availability, agricultural deployment potential, rainfall and weathering conditions, logistics access, and farmer/FPO aggregation potential.

Based on this state-wise screening, the following five states emerge as the most suitable for ERW deployment:

| Rank | State | Key Strengths |
| --- | --- | --- |
| 1 | Madhya Pradesh | Highest overall score; strong basalt, logistics, FPO network |
| 2 | Maharashtra | Strong Deccan basalt availability; good agricultural infrastructure |
| 3 | Gujarat | Good logistics and crop deployment potential |
| 4 | Karnataka | Suitable rainfall and weathering conditions |
| 5 | Telangana | Emerging FPO network and moderate basalt access |

Madhya Pradesh ranks first in the national screening and is selected as the primary state for ERW pilot deployment. The analysis then narrows to zone-level and district-level screening within MP.

## 2.2 Site Suitability Index (SSI) Scoring Framework

A weighted Site Suitability Index (SSI) is used to objectively identify the most suitable district-level locations. Each parameter is scored on a 1–5 scale and weighted by its relative importance to ERW performance.

SSI = 20% (Soil pH) + 25% (Basaltic Rock Availability) + 20% (Rainfall & Weather) + 20% (Transport Feasibility) + 15% (FPO/Farmer Aggregation)

Basaltic rock availability carries the highest weight (25%) because ERW requires large volumes of reactive silicate rock. Soil pH, rainfall, and transport are heavily weighted as they directly affect weathering rate, implementation cost, and net carbon removal. Farmer aggregation is included because ERW requires coordinated field application, repeated soil and water sampling, and long-term farmer participation.

### SSI Parameter Scoring Matrix

| Score | Suitability | Soil pH | Basalt Availability | Rainfall & Weather | Transport | FPO Support |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | Excellent | Acidic–neutral; high dissolution | Deccan basalt & quarry ecosystem nearby | Warm & moist; very high weathering | Quarry, crusher & road network ideal | Strong FPO & institutional support |
| 4 | Good | Neutral–mildly alkaline; workable | Basalt accessible within reasonable distance | Good rainfall & temperature balance | Good road network & quarry distance | Good agri network & FPO potential |
| 3 | Moderate | Mixed/moderately alkaline; slower | Some basaltic geology; sourcing possible | Moderate rainfall; workable with planning | Moderate logistics feasibility | Moderate farmer aggregation |
| 2 | Low | Highly alkaline; limited suitability | Limited access; longer transport required | Dry or uneven rainfall; slower weathering | Long distance or difficult terrain | Weak farmer aggregation |
| 1 | Poor | Poor soil chemistry; correction required | Weak or non-basaltic geology | Very low rainfall / poor moisture regime | Poor logistics for bulk rock dust | Very weak farmer network |

## 2.3 Zone-Level ESI Scores — Madhya Pradesh

Following the national-level selection of Madhya Pradesh, a zone-wise ERW Environmental Suitability Index (ESI) analysis is conducted across five MP zones to identify the priority pilot areas.

| Zone | Avg. ESI /100 | Category | Priority | Key Suitable Districts |
| --- | --- | --- | --- | --- |
| West MP | 73 | Very High | Priority 1 | Khandwa, Indore, Dhar, Dewas, Khargone |
| Central MP | 71 | High | Priority 2 | Narmadapuram, Harda, Sehore, Raisen, Bhopal |
| South MP | 64 | Medium-High | Priority 3 | Betul, Chhindwara, Pandhurna, Seoni, Balaghat |
| East MP | 46 | Low-Medium | Priority 4 | Narsinghpur, Jabalpur, Katni, Singrauli |
| North MP | 43 | Low | Priority 5 | Gwalior, Morena, Shivpuri, Sagar, Damoh |

West MP (ESI: 73/100) and Central MP (ESI: 71/100) are selected as the primary ERW pilot zones. Key districts — Khandwa, Indore, Dhar, Dewas, Khargone, Narmadapuram, Harda, and Sehore — are prioritised based on superior soil, basalt, rainfall, logistics, and farmer/FPO suitability scores.

# 3. Ground Operations

Ground operations cover the complete operational workflow from basalt quarry selection and rock powder procurement through to farmer onboarding, field application, and cost planning. The Khandwa district in West MP is selected as the primary operational zone.

## 3.1 Quarry Identification and Rock Powder Supply

The ERW pilot requires a reliable, high-quality basalt supply source within a feasible transport radius of the target farmland. The following quarry and crushing facilities in the Khandwa district have been identified as primary supply candidates:

| Source Point | Relevance to ERW Pilot | Verification Required |
| --- | --- | --- |
| Bhavsinghpura Basalt Quarry, Khandwa | Active basalt/metal stone quarry; 10.47 ha lease area; ~12 km from Khandwa town — ideal for low-distance ERW logistics. | Basalt quality test, powder particle size, supply capacity |
| Khandwa Stone Crusher LLP | Registered under mining and quarrying in Khandwa. Likely source for crushed basalt fines. | Crusher capacity, material type, rate per MT |
| Bansal Stone Crusher, Khandwa | Local crushed stone supplier in Khandwa; useful for initial market enquiry and rate benchmarking. | Material source, basalt confirmation, transport rate |
| Swaraj Stone Crusher, Khandwa | Listed metal stone supplier and service provider in Khandwa district. | Availability of basalt dust/fines, pricing |

Bhavsinghpura Basalt Quarry, Khandwa is identified as the primary supply source for the pilot, based on proximity, confirmed basalt geology, and suitable lease infrastructure.

## 3.2 Quarry Contact and Procurement Agreement

After selecting Bhavsinghpura Basalt Quarry as the primary source point, a structured procurement process will be executed in the following sequence:

- Step 1 — Identify Quarry POC: Contact the quarry lease holder, site manager, or local mining office representative to confirm material availability, powder quality, supply capacity, pricing, transport support, and required documentation.

- Step 2 — Sample Testing: Collect and analyze rock powder samples for mineral composition, Ca/Mg content, particle size distribution, carbon content, moisture, and heavy metal safety.

- Step 3 — Sign Pilot MoU/LOI: Formalize the supply intent through a Memorandum of Understanding or Letter of Intent.

- Step 4 — Execute Supply Agreement: Sign a formal rock powder supply agreement covering quantity commitments, quality standards, price per MT, delivery schedule, weighbridge slips, invoicing procedures, and rejection clauses.

## 3.3 FPO and Institution Mapping for Pilot Onboarding

Following quarry selection, nearby Farmer Producer Organizations (FPOs) and institutional partners are mapped based on road distance from the quarry, to minimize transport costs and streamline farmer onboarding.

| FPO / Institution | Location | Distance from Quarry | Transport Priority | Onboarding Recommendation |
| --- | --- | --- | --- | --- |
| KVK Khandwa | Jaswadi Road, Khandwa | ~12–15 km | Very High | First contact for technical support and soil testing |
| Pandhana Pashupalak Producer Co. Ltd. | Pandhana, Khandwa | ~30–35 km | High | Strong candidate for farmer onboarding |
| Nimadanchal Agriculture FPC Ltd. | Pandhana, Khandwa | ~30–35 km | High | Strong candidate for farmer cluster mapping |
| Food Grains Organic Producer Co. Ltd. | Jamni/Ashapur/Khalwa, Khandwa | To be verified | Medium | Feasible if distance and farmer cluster align with pilot radius |

KVK Khandwa is selected as the primary institutional partner for Phase 1, given its proximity (~12–15 km from quarry) and strong technical capacity. The pilot will initially engage 2 nearby Gram Panchayats through KVK support, reducing transport cost and simplifying field monitoring.

## 3.4 Transportation and Supply Cost Plan

Transportation will be handled through local truck vendors, keeping the quarry as a pure supply source. This local vendor model offers better cost control, rate negotiation flexibility, and easier truck availability management.

Note: The following estimates are based on assumed case-study values and must be verified through actual vendor quotations before procurement.

| Cost Head | Assumed Value |
| --- | --- |
| Material rate from quarry | ₹450 per MT |
| Loading charge at quarry | ₹50 per MT |
| Truck capacity | 16 MT per trip |
| Local transport vendor quote | ₹6,000 per trip |
| Transport cost per MT | ₹375 per MT |
| Unloading / handling cost | ₹40 per MT |
| Final landed cost per MT | ₹915 per MT |
| Total cost for 10,000 MT | ₹91.5 lakh |

## 3.5 Farmer Onboarding and Agreement Model

The pilot will focus on farmer clusters within a 20 km radius of the Khandwa quarry, creating an operational catchment of approximately 1,260 sq. km. Priority will be given to FPO-linked farmers in this zone to minimize transport costs and simplify field monitoring.

| Stage | Approach | Offer / Pay Basis | Purpose |
| --- | --- | --- | --- |
| Phase 1: Free Pilot | Onboard farmers within 20 km quarry radius via FPO/KVK support | Free rock powder + application + soil testing | Build trust and demonstrate ERW agronomic benefits |
| Phase 2: Participation Support | For farmers hesitant to join the free pilot | ₹500–₹1,000 per acre as one-time support | Encourage participation; cover farmer coordination effort |
| Phase 3: Formal Agreement | Sign agreement before rock powder application begins | Carbon credit ownership remains with project developer | Ensure clarity on land use, monitoring access, and credit rights |

Before rock powder application, each farmer will sign a simple participation agreement confirming the following:

- Land is being used for the ERW pilot during the specified project period.

- Field monitoring and soil sampling access will be granted to the project team.

- Carbon credit ownership remains with the project developer (unless separately negotiated).

- Farmers will receive free soil testing, technical guidance, and any agreed participation support.

## 3.6 Resources Required for the First 6 Months

The following resources must be secured before pilot implementation begins:

- Confirmed quarry point of contact and tested basalt rock powder supply

- KVK, FPO, and Gram Panchayat institutional support

- Field team (agronomists, field supervisors, data collectors)

- Accredited soil and rock testing laboratory

- Transport and rock powder spreading equipment

- Farmer onboarding and communication support

- GPS-based field data capture devices

- Sampling kits (soil, water, rock)

- Budget allocation for logistics, testing, labour, and MRV documentation

# 4. Testing, Sampling, and MRV Development

Testing and sampling follow a structured three-stage process: baseline testing before application, real-time monitoring during application, and post-application testing. Data from all three stages feeds directly into the Measurement, Reporting, and Verification (MRV) framework required for carbon credit generation.

## 4.1 Application Rate Decision

The pilot application rate is determined by two factors: soil pH and site suitability, and rock powder quality. The following tables guide rate selection.

### A. Soil pH-Based Application Rate

| Soil pH Result | ERW Suitability | Suggested Pilot Rate |
| --- | --- | --- |
| < 5.5 | Too acidic; caution required | 0–5 MT/ha |
| 5.5–6.2 | Moderately acidic; workable | 5–10 MT/ha |
| 6.2–7.2 | Best suitable range | 10–20 MT/ha (optimal) |
| 7.2–7.8 | Mildly alkaline | 5–10 MT/ha |
| 7.8–8.2 | Alkaline; limited use | 2–5 MT/ha |
| > 8.2 | Not recommended | Avoid / very small trial only |

### B. Rock Quality-Based Rate Adjustment

| Rock Quality | Condition | Rate Adjustment |
| --- | --- | --- |
| High Quality Basalt | Good Ca/Mg content, fine particle size, safe heavy metals | Use upper rate in range |
| Medium Quality Basalt | Average mineral composition and particle size | Use middle rate in range |
| Low Quality Basalt | Low reactivity or heavy metal concern | Use lower rate or avoid |

Based on the rate-selection framework and optimal site conditions in West MP, the pilot application rate is set at 20 MT/ha. At this rate, the 10,000 MT deployment covers approximately 500 hectares of farmland.

## 4.2 Composite Soil Sampling Method

Each soil sample will be prepared as a composite sample by collecting sub-samples from 5–15 nearby points within a 5–15 meter radius. Sub-samples are thoroughly mixed, labelled with a unique Sample ID, GPS coordinates, date, depth, and plot type, and then dispatched to the testing laboratory.

## 4.3 Three-Stage Testing Framework

### Stage 1: Baseline Testing — Before Application

Baseline testing records the original soil condition before any rock powder is applied. Samples are collected from both treatment plots and control plots.

Soil Parameters:

pH, electrical conductivity (EC), organic carbon, inorganic carbon, cation exchange capacity (CEC), soil texture, moisture, NPK, Ca, Mg, K, Na, and heavy metals.

Rock Powder Parameters:

Mineral composition, Ca/Mg content, particle size distribution, carbon content, moisture, and heavy metal safety profile.

### Stage 2: Application-Time Monitoring — During Application

This stage confirms that the correct quantity of rock powder is applied at the correct rate and location and creates a comprehensive application audit trail.

Records Collected:

Rock powder quantity and batch, application rate per hectare, GPS location of each plot size and boundaries, application date and time, photos and videos, farmer details, and crop type.

### Stage 3: Post-Application Testing — After Application

Post-application testing measures soil changes attributable to ERW and benchmarks results against baseline data and control plots.

Soil Parameters:

pH, EC, organic carbon, inorganic carbon, Ca, Mg, K, Na, CEC, heavy metals, and crop response/yield indicators.

Water/Leachate Parameters (where feasible):

pH, EC, alkalinity, bicarbonate/dissolved inorganic carbon (DIC), Ca, Mg, silicon, and heavy metals.

## 4.4 MRV Framework

All three testing stages generate the core data needed for Measurement, Reporting, and Verification (MRV). The MRV framework is designed to produce a defensible, third-party-verifiable carbon removal record.

| MRV Component | Data and Documentation Used |
| --- | --- |
| Measurement | Soil test results, rock powder quality data, quantities applied, GPS plot data |
| Reporting | Lab reports, application logs, farmer records, field photographs and videos |
| Verification | Unique sample IDs, batch records, GPS proof, control plot vs. treatment plot comparisons |

5. Data Analysis

Following field testing and sampling, all collected data is systematically analysed to estimate the carbon removal potential of the ERW pilot. The analysis pipeline converts field and laboratory data into a defensible, measurable CO₂ removal estimate suitable for MRV reporting.

## 5.1 Data Capture Framework

| Main Data Type | Sub-Type | Details |
| --- | --- | --- |
| 1. Soil & Rock Powder Data | Soil test data | pH, EC, organic carbon, inorganic carbon, Ca, Mg, K, Na, CEC, heavy metals |
|  | Rock powder data | Mineral composition, Ca/Mg content, particle size, carbon content, moisture, heavy metals |
| 2. Plot & Application Data | Control plot data | Untreated soil results for comparison with treated plots |
|  | Application data | Quantity applied, application rate, GPS location, date, rock powder batch number |
|  | Plot data | Plot size, treated area, control area, farm location, sampling point coordinates |
| 3. Field Observations | Field data | Crop type, yield response, rainfall, drainage condition, farmer details, field photos |

## 5.2 Data Analysis Approach

The collected data is analyzed across three comparative dimensions to isolate the true ERW impact:

- Baseline vs. Post-Application: Identifies changes in soil pH, cation concentrations, carbon content, and overall soil health attributable to ERW.

- Treatment Plot vs. Control Plot: Separates actual ERW-driven changes from background seasonal or farming-related variation.

- Rock Powder Quality vs. Soil Response: Quantifies how rock mineral composition, particle size, and application rate influenced weathering performance and carbon removal efficiency.

## 5.3 Final Analysis Outputs

The data analysis and modeling stage will generate the following deliverables for each pilot site:

- Estimated CO₂ removal from the pilot (expressed as tCO₂ removed per hectare and total for pilot area)

- Soil-health impact report comparing pre- and post-application conditions

- Treated vs. control plot comparison with statistical analysis

- Rock powder performance assessment (mineral efficiency and weathering rate)

- Net carbon removal estimates after deducting lifecycle emissions (transport, spreading, etc.)

- Packaged data report for MRV submission and future third-party verification

## 5.4 Pilot KPIs and Milestone Timeline

Pilot success will be monitored through the following monthly milestones and key performance indicators:

| Month | Key Milestone | KPIs and Success Criteria |
| --- | --- | --- |
| 1 | Partner & Quarry Setup | Quarry POC confirmed; KVK/FPO engaged; 2 Gram Panchayats shortlisted |
| 2 | Farmer Onboarding & Baseline Testing | Farmers onboarded with signed consent; treatment/control plots selected; baseline soil and rock testing completed |
| 3 | Application Planning | Final application rate confirmed; transport plan finalized; MRV format and GPS tracking system prepared |
| 4 | Field Application | Rock powder applied across target area; hectares covered confirmed; GPS photos, weighbridge slips, and application logs collected |
| 5 | Monitoring | Treatment vs. control plots monitored; farmer feedback collected; crop and soil response observed and documented |
| 6 | Post-Testing & MRV Output | Post-application testing completed; lab results benchmarked against baseline; safety check passed; initial CO₂ removal estimate prepared |

Overall pilot success is measured by: farmer onboarding rate, area covered (target: 500 ha), total rock powder applied (target: 10,000 MT), completion of all three testing stages, treatment vs. control comparison quality, soil safety confirmation, farmer acceptance rate, completeness of MRV records, and validity of initial CO₂ removal estimate.

# 6. Project Registration

Upon completion of testing, sampling, data analysis, and CO₂ removal modeling, the ERW pilot will be prepared for formal registration with a recognized carbon removal registry or standard body. Registration converts the pilot’s field data into a formally verified, credit-issuable carbon removal project.

## 6.1 Registration Documentation Package

The following documentation will be compiled and submitted for registration:

- Farm location data, GPS-defined area boundaries, and total hectares enrolled

- Rock powder source details (quarry, mineral composition, and supply chain records)

- Total quantity applied and per-hectare application rates

- All laboratory test reports (baseline, application-time, and post-application)

- Sampling data with unique sample IDs and GPS-linked proof

- MRV plan and methodology documentation

- CO₂ removal estimate and net emissions calculations

- Farmer records, signed participation agreements, and field photographs

- Application logs, weighbridge slips, and batch records

## 6.2 Registration Process

| Step | Action |
| --- | --- |
| 1 | Select a suitable carbon removal registry (e.g., Puro. Earth, Isometric, Gold Standard, or equivalent durable CDR standard) |
| 2 | Prepare the Project Design Document (PDD) incorporating all field, testing, and modeling data |
| 3 | Submit testing, sampling, MRV, and modeling data package to the selected registry |
| 4 | Undergo registry or independent third-party technical review |
| 5 | Address technical queries or additional data requests from the reviewing body |
| 6 | Receive project registration approval and prepare for first verification cycle |

Output: A registered ERW pilot project, ready for future verification and carbon credit issuance.

# Appendix: Documentation Q&A Cross-Reference

This appendix maps key project design questions to their corresponding sections in the report, providing a quick-reference guide for technical review and stakeholder queries.

| Question | Report Reference |
| --- | --- |
| Q1: Identify where in India ERW could work best, and why? Where should the pilot be situated? | Section 2 — Site Identification (national screening, SSI framework, MP zone analysis) |
| Q2: Create a comprehensive, action-oriented implementation plan for an ERW pilot. | Implementation Flow Overview + Sections 1–6 in full |
| Q2.1: Which modelling techniques reduce uncertainty in carbon sequestration quantification? | Section 5.4 — Pilot KPIs and Milestone Timeline; Section 4.4 — MRV Framework |
| Q2.2: Which specific quarries will supply the first 10,000 MT of rock powder? | Section 3.1 — Quarry Identification |
| Q2.2 (cont.): Who to contact and how to structure a procurement agreement? | Section 3.2 — Quarry Contact and Procurement Agreement |
| Q2.3: Which feedstock is best? (cost per ton, credits per ton, quality, etc.) | Section 4.1 — Application Rate Decision (soil pH-based and rock quality-based framework) |
| Q2.4: Which specific districts/Gram Panchayats would spread the first 10,000 MT? | Section 3.3 — FPO and Institution Mapping (Khandwa district, KVK, 2 Gram Panchayats) |
| Q2.4 (cont.): Operations within 100 km of quarries for LCA; restricted to 2 Gram Panchayats. | Section 3.3 — FPO Mapping (20 km catchment, 100 km radius constraint) |
| Q2.5: What are the criteria for geography selection? What feasibility tests are needed? | Section 2.2 — SSI Scoring Matrix; Section 4 — Testing, Sampling, and MRV |
| Q2.6: What resources are required for the first 6 months? What are the KPIs? | Section 3.6 — Resources Required; Section 5.4 — KPIs and Milestone Timeline |